## excel (8)
Project/Task | Phase | Start Time | Delta | Interrupt | Comment
/Non Project/PSP Fundamentals & Advanced/Program 3 | Planning | mar 07, 2017 01:43:45 PM | 89 | 18
/Non Project/PSP Fundamentals & Advanced/Program 3 | Planning | mar 07, 2017 03:48:15 PM | 22 | 0
/Non Project/PSP Fundamentals & Advanced/Program 3 | Planning | mar 07, 2017 10:27:27 PM | 24 | 0
/Non Project/PSP Fundamentals & Advanced/Program 3 | Planning | mar 07, 2017 11:33:52 PM | 23 | 0
/Non Project/PSP Fundamentals & Advanced/Program 3 | Planning | mar 08, 2017 06:11:05 AM | 13 | 0
/Non Project/PSP Fundamentals & Advanced/Program 3 | Design | mar 08, 2017 06:23:55 AM | 2 | 0
/Non Project/PSP Fundamentals & Advanced/Program 3 | Design | mar 08, 2017 06:45:34 AM | 15 | 0
/Non Project/PSP Fundamentals & Advanced/Program 3 | Design | mar 08, 2017 07:07:34 AM | 2 | 0
/Non Project/PSP Fundamentals & Advanced/Program 3 | Design | mar 08, 2017 07:17:59 AM | 25 | 0
/Non Project/PSP Fundamentals & Advanced/Program 3 | Design Review | mar 08, 2017 07:42:58 AM | 5 | 0
/Non Project/PSP Fundamentals & Advanced/Program 3 | Code | mar 08, 2017 07:47:36 AM | 96 | 10
/Non Project/PSP Fundamentals & Advanced/Program 3 | Code | mar 08, 2017 10:11:29 AM | 23 | 1
/Non Project/PSP Fundamentals & Advanced/Program 3 | Code | mar 08, 2017 10:42:53 AM | 5 | 0
/Non Project/PSP Fundamentals & Advanced/Program 3 | Code Review | mar 08, 2017 10:47:35 AM | 26 | 28
/Non Project/PSP Fundamentals & Advanced/Program 3 | Test | mar 08, 2017 11:42:42 AM | 1 | 0
/Non Project/PSP Fundamentals & Advanced/Program 3 | Postmortem | mar 08, 2017 11:42:43 AM | 0 | 0
/Non Project/PSP Fundamentals & Advanced/Program 3 | Test | mar 08, 2017 11:43:38 AM | 15 | 0
/Non Project/PSP Fundamentals & Advanced/Program 3 | Test | mar 08, 2017 12:08:39 PM | 29 | 4
/Non Project/PSP Fundamentals & Advanced/Program 3 | Postmortem | mar 08, 2017 12:42:07 PM | 52 | 1